Project Cost Estimate:  Application Development

Notes:    No overtime; Workday equals 8 hours

| Task | Unit | Multiplier | Duration (days) | Total Duration | Unit Cost | Extended Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1.2 Business Requirements |  |  |  |  |  |  |
| 1.2.1 Evaluate Existing Processes |  |  |  |  |  |  |
| Internal project Management | Hourly | 1 | 1 | 8 | $150.00 | $1,200.00 |
| Business Analyst | Hourly | 2 | 5 | 80 | $150.00 | $12,000.00 |
| 1.2.2 Evaluate Legacy Applications |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | 5 | 40 | $150.00 | $6,000.00 |
| Technical Analyst | Hourly | 1 | 3 | 24 | $150.00 | $3,600.00 |
| 1.2.3 Define New Business Rules |  |  |  |  |  |  |
| Business Analyst | Hourly | 2 | 2 | 32 | $150.00 | $4,800.00 |
| 1.2.4 Define New Workflow |  |  |  |  |  |  |
| Business Analyst | Hourly | 2 | 2 | 32 | $150.00 | $4,800.00 |
| 1.2.5 UI Requirements |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | 1.5 | 12 | $150.00 | $1,800.00 |
| Graphic Designer | Hourly | 1 | 5 | 40 | $85.00 | $3,400.00 |
| 1.2.6 Technology Requirements |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | .5 | 4 | $150.00 | $600.00 |
| Network Engineer | Hourly | 1 | 1 | 8 | $175.00 | $1,400.00 |
| 1.2.7 Business Requirements Documentation |  |  |  |  |  |  |
| Business Analyst | Hourly | 2 | 4 | 64 | $150.00 | $9,600.00 |
| Technical Analyst | Hourly | 1 | 1 | 8 | $150.00 | $1,200.00 |
| Network Engineer | Hourly | 1 | .5 | 4 | $175.00 | $700.00 |

| Task | Unit | Multiplier | Duration (days) | Total Duration | Unit Cost | Extended Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1.3 Application Architecture |  |  |  |  |  |  |
| 1.3.1 Functional Specifications |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | 4 | 32 | $150.00 | $4,800.00 |
| Senior Application Developer | Hourly | 1 | 4 | 32 | $175.00 | $5,600.00 |
| Application Developer | Hourly | 1 | 1 | 8 | $125.00 | $1,000.00 |
| Database Architect | Hourly | 1 | 1 | 8 | $150.00 | $1,200.00 |
| 1.3.2 Technical Specifications |  |  |  |  |  |  |
| Technical Analyst | Hourly | 1 | 1 | 8 | $150.00 | $1,200.00 |
| Network Engineer | Hourly | 1 | .5 | 4 | $175.00 | $700.00 |

| Task | Unit | Multiplier | Duration (days) | Total Duration | Unit Cost | Extended Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1.4 Application Development |  |  |  |  |  |  |
| 1.4.1 Code design document |  |  |  |  |  |  |
| Senior Application Developer | Hourly | 1 | 3 | 24 | $175.00 | $4,200.00 |
| 1.4.2 Code control system |  |  |  |  |  |  |
| Application Developer | Hourly | 1 | .25 | 2 | $125.00 | $250.00 |
| 1.4.3 Development Environment |  |  |  |  |  |  |
| Application Developer | Hourly | 1 | .25 | 2 | $125.00 | $250.00 |
| Network Engineer | Hourly | 1 | .25 | 2 | $175.00 | $350.00 |
| 1.4.4 UI Development |  |  |  |  |  |  |
| Graphic Designer | Hourly | 2 | 5 | 80 | $85.00 | $6,800.00 |
| 1.4.5 Code development |  |  |  |  |  |  |
| Senior Application Developer | Hourly | 1 | 20 | 160 | $175.00 | $28,000.00 |
| Application Developer | Hourly | 6 | 40 | 1,920 | $125.00 | $240,000.00 |
| Materials |  |  |  |  |  |  |
| 1.4.2.2 Software: Code Library license | Fixed | 1 |  |  | $500.00 | $500.00 |
| 1.4.3.3 Hardware: Development Server | Fixed | 1 |  |  | $3,500.00 | $3,500.00 |

| Task | Unit | Multiplier | Duration (days) | Total Duration | Unit Cost | Extended Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1.5 Testing |  |  |  |  |  |  |
| 1.5.1 Test Environment |  |  |  |  |  |  |
| Application Developer | Hourly | 1 | .25 | 2 | $125.00 | $250.00 |
| Network Engineer | Hourly | 1 | .25 | 2 | $175.00 | $250.00 |
| 1.5.2 Test Plan development |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | .5 | 4 | $150.00 | $600.00 |
| 1.5.3 Unit Testing |  |  |  |  |  |  |
| Application Developer | Hourly | 2 | 10 | 160 | $125.00 | $20,000.00 |
| 1.5.4 UAT |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | 2 | 16 | $150.00 | $2,400.00 |
| Application Developer | Hourly | 2 | 5 | 80 | $125.00 | $10,000.00 |
| 1.5.5 Results reporting & integration |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | 2 | 16 | $150.00 | $2,400.00 |
| Materials |  |  |  |  |  |  |
| 1.5.5 Software: Bug Tracking License | Fixed | 1 |  |  | $125.00 | $125.00 |
| 1.5.1 Software: Development SSL Certificate | Fixed | 1 |  |  | $75.00 | $75.00 |
| 1.5.1 Hardware: Test Server | Fixed | 1 |  |  | $3,500.00 | $3,500.00 |

| Task | Unit | Multiplier | Duration (days) | Total Duration | Unit Cost | Extended Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1.6 Deployment |  |  |  |  |  |  |
| 1.6.1 Production Data Migration |  |  |  |  |  |  |
| Database Architect | Hourly | 1 | 2 | 16 | $150.00 | $2,400.00 |
| Senior Application Developer | Hourly | 1 | .5 | 4 | $175.00 | $700.00 |
| 1.6.2 Operations switch over |  |  |  |  |  |  |
| Database Architect | Hourly | 2 | 1 | 16 | $150.00 | $2,400.00 |
| Senior Application Developer | Hourly | 1 | 1 | 8 | $175.00 | $1,400.00 |
| Application Developer | Hourly | 2 | 1 | 16 | $125.00 | $2,000.00 |
| Network Engineer | Hourly | 1 | 1 | 8 | $175.00 | $1,400.00 |
| Client Support Engineer | Hourly | 2 | 1 | 16 | $75.00 | $1,200.00 |
| 1.6.3 Documentation |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | 1 | 8 | $150.00 | $1,200.00 |
| Technical Writer | Hourly | 1 | 5 | 40 | $75.00 | $3,000.00 |
| 1.6.4 Training |  |  |  |  |  |  |
| Business Analyst | Hourly | 1 | 2 | 16 | $150.00 | $2,400.00 |
| Client Support Engineer | Hourly | 2 | 15 | 120 | $75.00 | $9,000.00 |
| Materials |  |  |  |  |  |  |
| 1.6.2.2 Software: Application Support software (DR/ backup) | Fixed | 1 |  |  | $1,500.00 | $1,500.00 |
| 1.6.2.2 Software: SSL certificate | Fixed | 1 |  |  | $375.00 | $375.00 |
| 1.6.2.1 Hardware: Production servers | Fixed | 3 |  |  | $4,200.00 | $12,600.00 |
| 1.6.2.1 Hardware: Rack Space | Fixed | 1 |  |  | $1,250.00 | $1,250.00 |

| Task Summary | Unit | Multiplier | Duration (days) | Total Duration | Unit Cost | Extended Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1.2 Business Requirements | Hourly |  |  |  |  | $51,100.00 |
| 1.3 Application Architecture | Hourly |  |  |  |  | $14,500.00 |
| 1.4 Application Development |  |  |  |  |  |  |
| Staff Resources | Hourly |  |  |  |  | $279,850.00 |
| Materials | Fixed |  |  |  |  | $4,000.00 |
| 1.5 Testing |  |  |  |  |  |  |
| Staff Resources | Hourly |  |  |  |  | $35,900.00 |
| Materials | Fixed |  |  |  |  | $3,700.00 |
| 1.6 Deployment |  |  |  |  |  |  |
| Staff Resources | Hourly |  |  |  |  | $27,100.00 |
| Materials | Fixed |  |  |  |  | $15,725.00 |
| Estimated Deployment Cost |  |  |  |  |  |  |
| Resources |  |  |  |  |  | $408,450.00 |
| Materials |  |  |  |  |  | $23,425.00 |