Corporate Event Planning – Work Breakdown Structure (WBS)

- Event Requirements Definition

  - Corporate Requirements

    - Event Objectives

    - Location

    - Amenities

      - Sound / Stage / AV / Internet

      - Food & Beverage service

      - Concierge services

      - Meeting space

      - Entertainment

      - Hotel guest services

    - Size

      - Preliminary guest list / attendance count

    - Date(s)

    - Budget

- Venue Selection

  - Site visit

  - Venue selection

  - Contract

  - Deposit

- Corporate

  - Insurance / liability review / update

  - Budget allocation

- Event Attendance

  - Marketing Materials

    - Print ads

      - Target media

      - Design

    - WWW updates

  - Invitations

    - Design

    - Review

    - Printing

    - Distribution

  - RSVP

    - RSVP process management

      - Online RSVP

      - Paper RSVP

  - Web development

  - Payment processing

  - Materials

    - Brochures

    - Saleable items

  - Transportation

    - To / from airport

    - To / from entertainment

- Registration Booth

  - Design

  - Display / Location

  - Staff schedule

  - Booth setup

  - Booth teardown and storage

- Event Planning

  - Staffing Plan

  - Guest Speakers

    - Identification

    - Communications

    - Scheduling

    - Remuneration

  - Entertainment

    - Identification

    - Communications

    - Scheduling

    - Remuneration

  - Room / venue scheduling

  - Technology

    - Requirements definition

    - Setup

    - Teardown

  - Meal Planning

    - Beverages / all day refreshments

    - Breakfast

    - Lunch

    - Mid morning / afternoon snack